## New - UAT Cutover Tasks
Task | Assigned To | Due By | Status | T&Q | Data Hub? | Completed On | Notes
Dev Model Prep Activities
Update notes (modules, line items), acts as documentation |  |  | Not Started
Delete unused lists, substes |  |  | Not Started
Delete unused modules |  |  | Not Started
Delete unused line items in modules. Careful with line items used in filters. |  |  | Not Started
Delete unused/duplicate actions |  |  | Not Started
Update functional area for modules |  |  | Not Started
Review summary methods and update to 'None' where applicable. |  |  | Not Started
Perform end-to-end unit testing |  |  | Not Started
Test Security (make sure all new modules have security applied) |  |  | Not Started
Cleanup/Organize Dashboards |  |  | Not Started
Create/Update Admin dashboards |  |  | Not Started
UAT Prep Activities
Model Creation
If the model does not already exist, Create new UAT/TEST Model by importing from Dev Model. If the Model exists, ALM Sync the changes from Dev Model. |  |  | Not Started
Set this new model to 'Deployed Mode' |  |  | Not Started
Update Source Model to point to models in respective workspace (e.g. TEST Data Hub, TEST <spoke model> etc.) |  |  | Not Started
Duplicate the App, set source model to the new TEST model. Remember to update the Links as well. |  |  | Not Started
User Access for UAT
Add UAT users to workspace |  |  | Not Started
Assign Role to users in model (If new roles need to be created, please create in DEV and ALM sync with TEST) |  |  | Not Started
Assign Read/Write access to the Selective Access lists. |  |  | Not Started
Production Lists Update
Delete members in all Production Lists and Re-import from Data Hub. If there are production lists unique to your model (i.e. not loaded from Data Hub), ensure to clean and update those lists as well. If error, fix the issue and ALM sync. |  |  | Not Started
Update subsets. Deleting members in the step above will clear the subsets which will need to be initialized. |  |  | Not Started
System Modules Update
If you have system modules (such as Lookup modules) that are referencing Production List members, deleting members above will clear the references in those list formatted line items. Please update the reference again in the TEST model. |  |  | Not Started
Non-Production Lists Update
When the TEST model is created by importing from DEV, the TEST model will automatically inherit the non-production list members. Hence, no action is required here. It is good practice to review non-production list members, and if you do need to upate members, update in DEV and ALM sync with TEST. |  |  | Not Started
Data Update (Data Hub and Flat Files)
To facilitate a clean start for Testing, delete data in all data and input modules. Deleting list members in the steps above takes care of this action item for the most part. If not, please manually clear data by entering '0' in the formula of the input line items and removing the '0' after. |  |  | Not Started
Run actions to load Data from Data Hub. Use Admin Dashboard |  |  | Not Started
Run actions to load from Flat Files. Use latest/updated flat file. Use Admin Dashboard (if you have any input/data modules which you need to pre-populate prior to testing) |  |  | Not Started
Data Validation
Validate data in all the DATA modules |  |  | Not Started
Data Automation
Set up data automation (if any) |  |  | Not Started
1. Data Hub to Spoke (Refresh pages to be 1 per model) |  |  | Not Started
2. Spoke to Spoke |  |  | Not Started
3. Spoke to External (Exports) |  |  | Not Started
Major Changes Added (Optional)
Assess YOY Org Changes needing reconfiguration/development |  |  | Not Started

## New - PROD Cutover Tasks
Task | Assigned To | Due By | Status | Completed On | Notes
Dev Model Prep Activities
Please see UAT cutover tasks for details. No action required for PROD cutover tasks as these steps need to be performed prior to UAT and fully tested prior to promoting to PROD. |  |  | Not Started
PROD Prep Activities
Model Creation
Create new Prod Model by importing from Dev Model. |  |  | Not Started
Set this new model to 'Deployed Mode' |  |  | Not Started
Now ALM Sync the changes from Dev Model. |  |  | Not Started
Update Source Model to point to models in respective workspace (e.g. PROD Data Hub, PROD <spoke model> etc.) |  |  | Not Started
Duplicate the App, set source model to the new PROD model. Remember to update the Links as well. |  |  | Not Started
User Access for PROD
Add PROD users to workspace |  |  | Not Started
Assign Role to users in model (If new roles need to be created, please create in DEV and ALM sync with PROD) |  |  | Not Started
Assign Read/Write access to the Selective Access lists. |  |  | Not Started
Production Lists Update
Delete members in all Production Lists and Re-import from Data Hub. If there are production lists unique to your model (i.e. not loaded from Data Hub), ensure to clean and update those lists as well. If error, fix the issue and ALM sync. |  |  | Not Started
Update subsets. Deleting members in the step above will clear the subsets which will need to be initialized. |  |  | Not Started
System Modules Update
If you have system modules (such as Lookup modules) that are referencing Production List members, deleting members above will clear the references in those list formatted line items. Please update the reference again in the PROD model. |  |  | Not Started
Non-Production Lists Update
When the PROD model is created by importing from DEV, the PROD model will automatically inherit the non-production list members. Hence, no action is required here. It is good practice to review non-production list members, and if you do need to upate members, update in DEV and ALM sync with PROD. |  |  | Not Started
Data Update (Data Hub and Flat Files)
To facilitate a clean start for planning, delete data in all data and input modules. Deleting list members in the steps above takes care of this action item for the most part. If not, please manually clear data by entering '0' in the formula of the input line items and removing the '0' after. |  |  | Not Started
Run actions to load Data from Data Hub. Use Admin Dashboard |  |  | Not Started
Run actions to load from Flat Files. Use latest/updated flat file. Use Admin Dashboard (if you have any input/data modules which you need to pre-populate prior to testing) |  |  | Not Started
Data Validation
Validate data in all the DATA modules |  |  | Not Started
Data Automation
Set up data autmation (if any) |  |  | Not Started
1. Data Hub to Spoke |  |  | Not Started
2. Spoke to Spoke |  |  | Not Started
3. Spoke to External (Exports) |  |  | Not Started
Major Changes Added (Optional)
Assess YOY Org Changes needing reconfiguration/development |  |  | Not Started

## Existing - UAT Cutover Tasks
Task | Assigned To | Due By | Status | Completed On | Notes
Dev Model Prep Activities
Update notes (modules, line items), acts as documentation |  |  | Not Started
Delete unused lists, substes |  |  | Not Started
Delete unused modules |  |  | Not Started
Delete unused line items in modules. Careful with line items used in filters. |  |  | Not Started
Delete unused/duplicate actions |  |  | Not Started
Update functional area for modules |  |  | Not Started
Review summary methods and update to 'None' where applicable. |  |  | Not Started
Perform end-to-end unit testing |  |  | Not Started
Test Security (make sure all new modules have security applied) |  |  | Not Started
Cleanup/Organize Dashboards |  |  | Not Started
Create/Update Admin dashboards |  |  | Not Started
UAT Prep Activities
Model Creation
Create TEST Model by importing from PROD Model. Note: This serves as a starting point to test enhancements/updates/bug fixes on the copy of the latest version of the PROD model. Besides testing new/updated features, you are also ensuring you perform NNIT (No Negative Impact Test), to ensure existing fuctionality is not broken. |  |  | Not Started
Set this new model to 'Deployed Mode' |  |  | Not Started
ALM sync the updates from DEV to TEST Model using the latest revision tag. |  |  | Not Started
Update Source Model to point to models in respective workspace (e.g. TEST Data Hub, TEST <spoke model> etc.) |  |  | Not Started
Update the Test App to incorporate the changes. Avoid duplicating the entire app, this will cause loss of Favorites, will disconnect the existing My Pages to apps, URL shortcuts will get invalidated. |  |  | Not Started
User Access for UAT
Add UAT users to workspace |  |  | Not Started
Assign Role to users in model (If new roles need to be created, please create in DEV and ALM sync with TEST) |  |  | Not Started
Assign Read/Write access to the Selective Access lists. |  |  | Not Started
Production Lists Update
Delete members in only NEW Production Lists (that don't currenty exist in PROD model and were newly added) and Re-import from Data Hub. If there are NEW production lists unique to your model (i.e. not loaded from Data Hub), ensure to clean and update those lists as well. If error, fix the issue and ALM sync. |  |  | Not Started
Update subsets, where necessary. Deleting members from the NEW production lists in the step above will clear the subsets which will need to be initialized. |  |  | Not Started
System Modules Update
If you have system modules (such as Lookup modules) that are referencing Production List members, deleting members above will clear the references in those list formatted line items. Please update the reference again in the TEST model. |  |  | Not Started
Non-Production Lists Update
Once you have ALM synched from DEV using the latest revision tag, the TEST model will automatically inherit the non-production list members. Hence, no action is required here. It is good practice to review non-production list members, and if you do need to upate members, update in DEV and ALM sync with TEST. |  |  | Not Started
Data Update (Data Hub and Flat Files)
To facilitate a clean start for Testing, delete data in only NEW data and input modules (that don't currenty exist in PROD model and were newly added). Deleting list members in the steps above takes care of this action item for the most part. If not, please manually clear data by entering '0' in the formula of the input line items and removing the '0' after. Note: Do not delete existing production data, as you still need that to perform NNIT (e.g. data validation) to ensure exisiting functionality is not broken and no data was lost post ALM sync. |  |  | Not Started
Run actions to load Data from Data Hub. Use Admin Dashboard |  |  | Not Started
Run actions to load from Flat Files. Use latest/updated flat file. Use Admin Dashboard (if you have any input/data modules which you need to pre-populate prior to testing) |  |  | Not Started
Data Validation
Validate data in all the DATA modules |  |  | Not Started
Data Automation
Set up data autmation (if any) |  |  | Not Started
1. Data Hub to Spoke |  |  | Not Started
2. Spoke to Spoke |  |  | Not Started
3. Spoke to External (Exports) |  |  | Not Started
Major Changes Added (Optional)
Assess YOY Org Changes needing reconfiguration/development |  |  | Not Started

## Existing - PROD Cutover Tasks
Task | Assigned To | Due By | Status | Completed On | Notes
Dev Model Prep Activities
Please see UAT cutover tasks for details. No action required for PROD cutover tasks as these steps need to be performed prior to UAT and fully tested prior to promoting to PROD. |  |  | Not Started
PROD Prep Activities
Model Creation
Before you begin, Copy and Archive the existing PROD model. This is your backup and helps you re-instate the PROD model to previous state incase of any loss of data. Evaluate if you need to export data prior to synching the structural changes from DEV, so that you can re-import it to avoid loss of data (required when the dimensionality of a Data/Input module changes). Communicate to end users (and potentially take model offline) |  |  | Not Started
Now ALM Sync the changes from Dev Model. |  |  | Not Started
Update Source Model to point to models in respective workspace (e.g. PROD Data Hub, PROD <spoke model> etc.) |  |  | Not Started
Update the Prod App to incorporate the changes. Avoid duplicating the entire app, this will cause loss of Favorites, will disconnect the existing My Pages to apps, URL shortcuts will get invalidated. |  |  | Not Started
User Access for PROD
Add PROD users to workspace |  |  | Not Started
Assign Role to users in model (If new roles need to be created, please create in DEV and ALM sync with PROD) |  |  | Not Started
Assign Read/Write access to the Selective Access lists. |  |  | Not Started
Production Lists Update
Delete members in only NEW Production Lists (that don't currenty exist in PROD model and were newly added) and Re-import from Data Hub. If there are NEW production lists unique to your model (i.e. not loaded from Data Hub), ensure to clean and update those lists as well. If error, fix the issue and ALM sync. |  |  | Not Started
Update subsets, where necessary. Deleting members from the NEW production lists in the step above will clear the subsets which will need to be initialized. |  |  | Not Started
System Modules Update
If you have system modules (such as Lookup modules) that are referencing Production List members, deleting members above will clear the references in those list formatted line items. Please update the reference again in the TEST model. |  |  | Not Started
Non-Production Lists Update
Once you have ALM synched from DEV using the latest revision tag, the PROD model will automatically inherit the non-production list members. Hence, no action is required here. It is good practice to review non-production list members, and if you do need to upate members, update in DEV and ALM sync with PROD. |  |  | Not Started
Data Update (Data Hub and Flat Files)
To facilitate a clean start for Planning, delete data in only NEW data and input modules (that don't currenty exist in PROD model and were newly added). Deleting list members in the steps above takes care of this action item for the most part. If not, please manually clear data by entering '0' in the formula of the input line items and removing the '0' after. Note: Do not delete any existing production data! Ensure this step is thoroughly tested in TEST model and NNIT is successful. |  |  | Not Started
Run actions to load Data from Data Hub. Use Admin Dashboard |  |  | Not Started
Run actions to load from Flat Files. Use latest/updated flat file. Use Admin Dashboard (if you have any input/data modules which you need to pre-populate prior to testing) |  |  | Not Started
Data Validation
Validate data in all the DATA modules |  |  | Not Started
Data Automation
Set up data autmation (if any) |  |  | Not Started
1. Data Hub to Spoke |  |  | Not Started
2. Spoke to Spoke |  |  | Not Started
3. Spoke to External (Exports) |  |  | Not Started
Major Changes Added (Optional)
Assess YOY Org Changes needing reconfiguration/development |  |  | Not Started